## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | Milestone 1 | Q&A | MUST HAVE |  | Rajalakshmi P | 3- Completed
2 | 2 | Milestone 2 Task 1 | 1) What is an LLM, and how does it work at a high level? Understand tokens → embeddings → Transformer → attention → next-token prediction. 2) What is a token in an LLM? How is text converted into tokens? Understand why "Hello world" is not necessarily treated as two tokens and why token count matters. 3) What is a context window? Why is it important when processing annual reports? Understand the maximum amount of information an LLM can consider in a request and why long PDFs cannot simply be sent entirely to the model. 4) What is the Transformer architecture, and why is it important for LLMs? Learn the basic idea of self-attention, query, key, value, and positional information. 5) What is self-attention in a Transformer? Be able to explain how the model determines which words/tokens are important in relation to other tokens. 6) What is prompting? What makes a good prompt? Understand system prompts, user prompts, instructions, context, examples, constraints, and output format. 7) What is temperature in an LLM? What happens when you increase or decrease it? Understand the relationship between temperature and randomness/creativity, especially why financial analysis would generally require controlled outputs. 8) What are hallucinations in LLMs? Why are they dangerous in financial applications? Understand why an LLM can produce a confident but unsupported financial number or statement. 9) How does an LLM generate an answer? Understand the basic flow: Input → tokens → model → probability distribution → next token → repeated until response is generated. 10) What are the limitations of LLMs, and how can we reduce them in a financial research system? This is especially important for our project. You should connect the answer to RAG, source citations, structured outputs, tool calling, validation, and grounding. | SHOULD HAVE |  | Rajalakshmi P | 3- Completed
3 | 3 | Milestone 2 Task 2 | 1. Study synthetic user research concepts, LLM persona simulation techniques, and behavioral modeling approaches. 2. Design system architecture, agent roles, persona data model, and experiment workflow. 3. Develop experiment workspace — users define product description, target audience, and research objectives. 4. Build Persona Generation Agent — generates diverse synthetic personas with name, age, occupation, personality traits, behavioral patterns, and psychological profile displayed as visual persona cards. 5. Implement Persona Memory and Consistency Module — each persona maintains consistent attributes, opinions, and prior conversation context across multi-turn interactions | MUST HAVE |  | Rajalakshmi P | 3- Completed
4 | 4 | Milestone 3 | 1. Build Survey Mode — user defines questions, all personas generate responses simultaneously, displayed side-by-side for comparison. 2. Validate persona consistency and response realism across multiple question types and product domains. 3. Test Survey Mode across diverse persona sets and product categories using sample experiment scenarios. 4. Build Interview Mode — conversational interface where user asks questions and selected persona responds in character, maintaining memory and behavioral consistency across turns. 5. Develop Insight Extraction Agent — analyzes all survey and interview responses, surfaces recurring themes, sentiment breakdown, agreement patterns, and behavioral trends. 6. Implement &quot;Would use this product?&quot; scoring — aggregated across persona segments with reasoning per persona group. 7. Validate insight extraction quality and theme relevance across varied experiment scenarios. | MUST HAVE |  | Rajalakshmi P | 3- Completed
5 | 5 | Milestone 4 | 1. Build Insights and Experiment Results Dashboard — displays theme clusters, sentiment breakdown, key persona quotes, and product validation scores visually. 2. Develop Research Report Generation Module — compiles persona profiles, response highlights, insight summary, and validation scoring into a structured downloadable PDF. 3. Conduct end-to-end testing across persona generation, both simulation modes, insight extraction, and report generation. | MUST HAVE |  | Rajalakshmi P | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | Milestone 1 | 1) What is an LLM, and how does it work at a high level? Understand tokens → embeddings → Transformer → attention → next-token prediction. 2) What is a token in an LLM? How is text converted into tokens? Understand why "Hello world" is not necessarily treated as two tokens and why token count matters. 3) What is a context window? Why is it important when processing annual reports? Understand the maximum amount of information an LLM can consider in a request and why long PDFs cannot simply be sent entirely to the model. 4) What is the Transformer architecture, and why is it important for LLMs? Learn the basic idea of self-attention, query, key, value, and positional information. 5) What is self-attention in a Transformer? Be able to explain how the model determines which words/tokens are important in relation to other tokens. 6) What is prompting? What makes a good prompt? Understand system prompts, user prompts, instructions, context, examples, constraints, and output format. 7) What is temperature in an LLM? What happens when you increase or decrease it? Understand the relationship between temperature and randomness/creativity, especially why financial analysis would generally require controlled outputs. 8) What are hallucinations in LLMs? Why are they dangerous in financial applications? Understand why an LLM can produce a confident but unsupported financial number or statement. 9) How does an LLM generate an answer? Understand the basic flow: Input → tokens → model → probability distribution → next token → repeated until response is generated. 10) What are the limitations of LLMs, and how can we reduce them in a financial research system? This is especially important for our project. You should connect the answer to RAG, source citations, structured outputs, tool calling, validation, and grounding. | 2026-09-07 | 2026-09-07 | Divyanshu kumar | Coding | 3- Completed | 10
2 | Milestone 2 Task 1 | Choose the product, features and target market. | 2026-09-07 | 2026-09-08 | Divyanshu kumar | Integration Test | 3- Completed | 5
3 | Milestone 2 Task 2 | 1. Study synthetic user research concepts, LLM persona simulation techniques, and behavioral modeling approaches. 2. Design system architecture, agent roles, persona data model, and experiment workflow. 3. Develop experiment workspace , users define product description, target audience, and research objectives. 4. Build Persona Generation Agent, generates diverse synthetic personas with name, age, occupation, personality traits, behavioral patterns, and psychological profile displayed as visual persona cards. 5. Implement Persona Memory and Consistency Module , each persona maintains consistent attributes, opinions, and prior conversation context across multi-turn interactions. | 2026-09-15 | 2026-09-17 | Divyanshu kumar | Build | 3- Completed
4 | Milestone 3 | 1. Build Survey Mode — user defines questions, all personas generate responses simultaneously, displayed side-by-side for comparison. 2. Validate persona consistency and response realism across multiple question types and product domains. 3. Test Survey Mode across diverse persona sets and product categories using sample experiment scenarios. 4. Build Interview Mode — conversational interface where user asks questions and selected persona responds in character, maintaining memory and behavioral consistency across turns. 5. Develop Insight Extraction Agent — analyzes all survey and interview responses, surfaces recurring themes, sentiment breakdown, agreement patterns, and behavioral trends. 6. Implement &quot;Would use this product?&quot; scoring — aggregated across persona segments with reasoning per persona group. 7. Validate insight extraction quality and theme relevance across varied experiment scenarios. | 2026-09-26 | 2026-09-28 | Divyanshu kumar | Regression Test | 3- Completed
5 | Milestone 4 | 1. Build Insights and Experiment Results Dashboard — displays theme clusters, sentiment breakdown, key persona quotes, and product validation scores visually. 2. Develop Research Report Generation Module — compiles persona profiles, response highlights, insight summary, and validation scoring into a structured downloadable PDF. 3. Conduct end-to-end testing across persona generation, both simulation modes, insight extraction, and report generation. | 2026-10-12 | 2026-09-15 | Divyanshu kumar | Others | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2026-09-07 | Q&A | Completed
2 | 2026-09-07 | Choose the product, features and target market. | Completed
3 | 2026-09-15 | 1. Study synthetic user research concepts, LLM persona simulation techniques, and behavioral modeling approaches. 2. Design system architecture, agent roles, persona data model, and experiment workflow. 3. Develop experiment workspace — users define product description, target audience, and research objectives. 4. Build Persona Generation Agent — generates diverse synthetic personas with name, age, occupation, personality traits, behavioral patterns, and psychological profile displayed as visual persona cards. 5. Implement Persona Memory and Consistency Module — each persona maintains consistent attributes, opinions, and prior conversation context across multi-turn interactions. | Completed
4 | 2026-09-26 | 1. Build Survey Mode — user defines questions, all personas generate responses simultaneously, displayed side-by-side for comparison. 2. Validate persona consistency and response realism across multiple question types and product domains. 3. Test Survey Mode across diverse persona sets and product categories using sample experiment scenarios. 4. Build Interview Mode — conversational interface where user asks questions and selected persona responds in character, maintaining memory and behavioral consistency across turns. 5. Develop Insight Extraction Agent — analyzes all survey and interview responses, surfaces recurring themes, sentiment breakdown, agreement patterns, and behavioral trends. 6. Implement &quot;Would use this product?&quot; scoring — aggregated across persona segments with reasoning per persona group. 7. Validate insight extraction quality and theme relevance across varied experiment scenarios | Completed
5 | 2026-10-12 | 1. Build Insights and Experiment Results Dashboard — displays theme clusters, sentiment breakdown, key persona quotes, and product validation scores visually. 2. Develop Research Report Generation Module — compiles persona profiles, response highlights, insight summary, and validation scoring into a structured downloadable PDF. 3. Conduct end-to-end testing across persona generation, both simulation modes, insight extraction, and report generation. | Completed

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Milestone 1 | 2026-09-07 | 2026-09-07 | Divyanshu kumar | 2026-09-07 | 2026-09-07 | Completed | Completed
2 | Milestone 2 Task 1 | 2026-09-07 | 2026-09-07 | Divyanshu kumar | 2026-09-07 | 2026-09-07 | Completed | Completed
3 | Milestone 2 Task 2 | 2026-09-15 | 2026-09-20 | Divyanshu kumar | 2026-09-15 | 2026-09-20 | Completed | Completed
4 | Milestone 3 | 2026-09-26 | 2026-10-03 | Divyanshu kumar | 2026-09-26 | 2026-10-03 | Completed | Completed
5 | Milestone 4 | 2026-10-12 | 2026-10-17 | Divyanshu kumar | 2026-10-12 | 2026-10-17 | Completed | Completed